## Project Information
PROJECT BASIC INFORMATION
Project Name	Huntd
Name of Product	The best app for hiring web3 developers.
	Links	Test plan	Permission table	RTM
		Jira	TestRail WEB	TestRail Mobile
Product Description	Huntd is a comprehensive job search and application tracking app designed to assist job seekers in their quest for employment. With its user-friendly interface and powerful features, this app is essential for individuals actively seeking job opportunities.
Project Description	Mission of the project	Conduct testing to verify the quality of the web and mobile application.
		Ensure the application is released without defects.
	Project output product	Test Summary report and Defects evaluation
	Project Type	Testing
Project Duration	Start date	2026/01/21	End date	2026/01/28
Test Objectives	The test objectives are the functionality of the web version and mobile version of the “Huntd”. The project focuses on the possibility to interact with the main objects of the website and app.
	For the web version, testing is planned to cover the registration, login, and password recovery processes, including input validations and system messages. Special attention will be given to the functionality for creating, editing, and deleting job vacancies, as well as managing applications for them. Testing also includes job search and filtering features, such as sorting, pagination, and saved searches, to ensure correctness and usability when working with large amounts of data.
	For the mobile version, the main testing objective is to verify key business scenarios, including onboarding, login, job search, applying for a job, and user profile management. Testing will also cover correct rendering on different devices and operating systems, application stability, navigation, and gesture interactions. Where applicable, offline functionality and notification handling will be verified. Particular attention will be paid to performance and overall stability of the mobile application.

## Test Summary
Execution Rate for Huntd Web app					Execution Rate for Huntd mobile app
Executed test cases		258	100%					Executed test cases		68	100%
Passed		247	96%					Passed		62	91%
Failed		11	4%					Failed		6	9%

Huntd Web bugs by Priority					Huntd Mobile bugs by Priority
Critical		2	29%					Critical		3	100%
High		2	29%					High		0	0%
Medium		2	29%					Medium		0	0%
Low		1	14%					Low		0	0%

Web features					Mobile features
No.	Features	Tests	Passed		Failed				No.	Features	Tests	Passed		Failed
1	Main page	26	25	96%	1	4%			1	Application	3	3	100%	0	0%
2	Candidates list	20	20	100%	0	0%			2	Sign In	9	9	100%	0	0%
3	Sign Up	87	82	94%	5	6%			3	Sign Up	22	22	100%	0	0%
4	Sign In	22	20	91%	2	9%			4	Profile	31	27	87%	4	13%
5	Chats	24	24	100%	0	0%			5	Chats	3	1	33%	2	67%
6	Profile	26	26	100%	0	0%			6				#DIV/0!		#DIV/0!
7	Footer	31	29	94%	2	6%			7				#DIV/0!		#DIV/0!
8	Web3 companies and Jobs	16	15	94%	1	6%			8				#DIV/0!		#DIV/0!
	Latest (Coverage)	252	241	96%	11	4%				Latest (Coverage)	68	62	91%	6	9%